## Summary
Section | Purpose
Functional Testing | Ensure all features work properly
UI/UX Testing | Validate layout, accessibility and visuals
Performance Testing | Measure speed, scalability, and reliability
Security Testing | Ensure data protection and input safety
Localization Testing | Verify readiness across regions and languages
UAT | End-user acceptance validation
QA Workflow | Define QA execution process
Reporting Metrics | Track and monitor QA metrics
Timeline | Map weekly QA phases
Final Checklist | Ensure launch readiness

## Functional
Test ID | Feature / Area | Test Scenario | Expected Result | Assigned To | Status (Pass/Fail) | Comments
F-01 | Data Upload | Upload .xlsx and .csv files | Valid files accepted; invalid ones rejected
F-02 | Chart Generation | Generate different chart types | Correct chart renders instantly
F-03 | Export | Download chart as PNG/PDF | File downloads successfully
F-04 | Error Handling | Upload corrupted file | Friendly error displayed
F-05 | Data Privacy | Check if data stored post-session | File deleted after use

## UI_UX
Test ID | Feature / Area | Test Scenario | Expected Result | Assigned To | Status (Pass/Fail) | Comments
U-01 | Layout Consistency | Check design on all browsers | Aligned elements, proper colors
U-02 | Responsive Design | Resize and test on mobile | Perfect scaling and readability
U-03 | Accessibility | Tab navigation, alt text check | Accessible for all users
U-04 | Brand Consistency | Verify LH IdeaCraft colors | Matches black–orange theme
U-05 | CTA Validation | Click all buttons and links | CTAs work properly

## Performance
Test ID | Feature / Area | Test Scenario | Expected Result | Assigned To | Status (Pass/Fail) | Comments
P-01 | Load Test | Simulate 100–500 concurrent users | Stable performance
P-02 | File Upload Stress | Upload 50 large files | No crash or timeout
P-03 | API Latency | Measure response time | < 3 seconds average
P-04 | Render Speed | Measure chart generation time | Charts load under 2 sec
P-05 | Global Access | Test from different countries | Acceptable latency globally

## Security
Test ID | Feature / Area | Test Scenario | Expected Result | Assigned To | Status (Pass/Fail) | Comments
S-01 | File Validation | Try malicious file upload | Upload blocked
S-02 | HTTPS | Verify SSL certificate | Valid SSL active
S-03 | Input Sanitization | Attempt script injection | No execution allowed
S-04 | Data Retention | Inspect logs post upload | No residual files
S-05 | User Privacy | Review policy compliance | Meets GDPR standards

## Localization
Test ID | Feature / Area | Test Scenario | Expected Result | Assigned To | Status (Pass/Fail) | Comments
L-01 | Time Zone | Check timestamps globally | Correct local times
L-02 | Encoding | Upload Unicode data | Displays correctly
L-03 | Currency/Date | Different regional formats | Formats display properly
L-04 | Geo Access | Access via VPN | Loads without region issues
L-05 | CDN Performance | Check content delivery | Images/charts load fast

## UAT
Test ID | Feature / Area | Test Scenario | Expected Result | Assigned To | Status (Pass/Fail) | Comments
UAT-01 | New User Flow | Signup → Upload → Generate Chart | End-to-end works fine
UAT-02 | Returning User | Repeat flow, verify caching | Loads faster
UAT-03 | Public Access | No login access | Works without auth
UAT-04 | Power User | Stress test with multiple files | No crash
UAT-05 | Feedback | Submit feedback form | Saved successfully

## QA_Workflow
Phase | Activity | Owner | Deliverable
Test Design | Create all test cases and assign ownership | QA Intern | Test case sheet
Execution | Execute and log results | All Devs + QA | Bug list with priority
Regression | Re-test fixed bugs | QA Intern | Updated pass/fail matrix
UAT | Run full user flow tests | You + Testers | UAT report
Final Sign-off | Compile reports and get approval | You | Go-live checklist

## Reporting
Metric | Goal | Current | Comments
Pass Rate | ≥ 95%
Crash Rate | < 1%
Avg Load Time | < 3 sec
User Feedback Score | ≥ 8/10
File Success Rate | ≥ 99%

## Timeline
Week | Focus | Deliverables
Week 1 (Oct 21–27) | Functional + UI Testing | Feature validation reports
Week 2 (Oct 28–Nov 3) | Performance + Security | Load + API test logs
Week 3 (Nov 4–10) | UAT + Localization | Multi-region feedback results
Week 4 (Nov 11–17) | Regression + Final QA | UAT sign-off sheet
Week 5 (Nov 18–24) | Launch Prep | Go-live checklist